A STRATEGIC PARTNERSHIP PROPOSAL FOR THE LAUNCH OF THE MT. MONICA CHOIR ALBUM

Title: A Strategic Partnership for the Launch of the Mt. Monica Choir Album: "UKRISTO NI UMOJA"

Prepared For: The Management, Wasafi Media Prepared By:The Leadership, Mt. Monica Choir Date:21 September 2025

Table of Contents

1. Executive Summary

2. Problem Statement / Opportunity

3. Proposed Solution & Partnership Overview

4. Our Qualifications: The Mt. Monica Choir

5. Project Timeline & Key Milestones

6. Pricing & Budget Outline

7. Terms and Conditions

8. Agreement

1. Executive Summary

Mt. Monica Choir, a renowned gospel ensemble, has produced a powerful new album of contemporary Christian music, "Harmony of Faith." We are seeking a strategic partnership with Wasafi Media, a leader in entertainment and media production, to launch this album through a major concert event.

This proposal outlines a mutually beneficial partnership where Wasafi Media provides the financial backing and logistical expertise to produce a high-quality concert. In return, Wasafi will gain access to the lucrative and loyal gospel market, receive a significant share of the album and concert profits, and enhance its brand portfolio with uplifting, family-friendly content.

We believe this collaboration is a unique opportunity to create a commercially successful and culturally significant event.

2. Problem Statement / Opportunity

The Mt. Monica Choir possesses a finished product a professionally recorded album with high potential for market success. However, we lack the capital and large-scale event management resources required to organize a launch concert of the caliber this album deserves. Without a major launch event, the album's reach will be limited to our immediate community, missing a significant commercial and evangelical opportunity.

This presents a clear opportunity for Wasafi Media

- Market Expansion: Tap into the vast and underserved gospel and Christian music audience in Tanzania and beyond.

- Revenue Generation: Profit sharing from ticket sales, album sales (physical and digital), and potential streaming revenue.

- Brand Enhancement: Associate the Wasafi brand with positive, inspirational, and community-building content, expanding its public image.

4. Content Acquisition: Secure exclusive rights to broadcast and distribute a major gospel music event.

3. Proposed Solution & Partnership Overview

We propose that Wasafi Media becomes the official financier and producer of the "UKRISTO NI UMOJA" Album Launch Concert.

Roles and Responsibilities:

Mt. Monica Choir will provide

- The finished album master.

- The primary performing artist (the choir and soloists).

3. Marketing support through our church and community networks.

4. Creative input on the program and stage design to ensure alignment with our message.

Wasafi Media will provide

- Full Funding: Cover all costs associated with the concert (see Budget Outline).

2. Event Production: Secure a venue, manage stage setup, sound, lighting, and backline.

3. Promotion & Marketing: Leverage its powerful media platforms (TV, radio, social media) to promote the event nationally.

- Ticketing & Sales: Manage ticket sales through its established networks.

5. Media Coverage: Film and broadcast the concert for future TV specials or digital content.

4. Our Qualifications: The Mt. Monica Choir

Mt. Monica Choir is not just a musical group; we are a ministry with a track record of excellence.

- Musical Excellence: Comprised of dedicated and talented vocalists and musicians.

- Proven Product: We have already invested in the high-quality recording, mixing, and mastering of the "UKRISTO NI UMOJA" album, demonstrating our commitment and belief in the project.

- Captive Audience: We have a built-in support base of hundreds of church members and a wider network of gospel music fans.

- Professionalism: We are organized and prepared to work diligently as partners to ensure the success of this event.

5.Project Timeline & Key Milestones

| Phase | Activity | Estimated Timeframe |
| --- | --- | --- |
| Phase 1: Planning | Contract Signing, Initial Creative Meetings | 2 Weeks |
| Phase 2: Pre-Production | Venue Booking, Finalizing Budget, Marketing Campaign Launch | 4 Weeks |
| Phase 3: Production | Rehearsals, Technical Setup, Media Promotions | 3 Weeks |
| Phase 4: Execution | Concert Day | 1 Day |
| Phase 5: Post-Event | Settlement of Accounts, Media Distribution, Review | 2 Weeks |

Total Project Timeline: Approximately 10-12 Weeks from agreement signing.

6. Pricing & Budget Outline

The following is a preliminary estimate for the concert production. A detailed budget will be developed jointly upon agreement.

| Item | Estimated Cost (TZS) | Notes |
| --- | --- | --- |
| Venue Rental |  | For a 500-1,000 capacity auditorium |
| Sound & Lighting |  | Professional grade for a high-quality experience |
| Backline & Instruments |  |  |
| Marketing & Promotion |  | Social media ads, radio spots, flyers |
| Staff & Security |  | Event staff, ushers, security personnel |
| Artiste Logistics |  | Transport, accommodation, hospitality |
| Contingency (10%) |  | For unforeseen expenses |
| Total Estimated Budget |  |  |

Revenue Sharing Proposal (To be negotiated):

- Concert Ticket Sales: ......% Wasafi / .......% Mt. Monica

- Album Sales at Event: .......% Mt. Monica / ......% Wasafi

- Post-Event Digital Sales/Streaming: .......% Wasafi / ......% Mt. Monica (subject to distribution deals)

7. Terms and Conditions

- Intellectual Property: Mt. Monica Choir retains all copyrights to the album's musical compositions and recordings. Wasafi Media receives a license to use the material for promoting and broadcasting this specific event.

- Budget Management: Wasafi Media will manage the budget, with regular financial updates provided to the choir's leadership.

- Creative Control: While Wasafi leads production, both parties must mutually agree on the creative direction and program to maintain the artistic and spiritual integrity of the event.

4. Force Majeure: Standard clauses for unforeseen circumstances that prevent the event from occurring.

8. Agreement

This proposal signifies our sincere interest in partnering with Wasafi Media. We are confident that this collaboration will be a resounding success, delivering financial returns and positive cultural impact.

We eagerly await the opportunity to discuss this proposal further.

Signatures:

---

For Mt. Monica Choir

Name:[Name of Choir Leader]

Title:Choir Director

Date:

---

For Wasafi Media

Name:

Title:

Date: