A STRATEGIC PARTNERSHIP PROPOSAL FOR THE LAUNCH OF THE “TAMASHA LA UKRISTO NI UMOJA”CONCERT.

Title: A Strategic Partnership for the Launch of the Mt. Monica Choir Concert: "TAMASHA LA UKRISTO NI UMOJA"

Prepared For: The Management, Wasafi Media

Prepared By:The Leadership, Mt. Monica Choir

Date:24 September 2025

Table of Contents.

1. Executive Summary

2. Problem Statement / Opportunity

3. Proposed Solution & Partnership Overview

4. Our Qualifications: The Mt. Monica Choir

5. Project Timeline & Key Milestones

6. Pricing & Budget Outline

7. Terms and Conditions

8. Agreement

1. Executive Summary

Mt. Monica-Makuburi (KMM), a renowned and respected gospel ensemble, has produced a powerful new album of contemporary Christian music titled "UKRISTO NI UMOJA." To mark this milestone, we are seeking a strategic partnership with Wasafi Media to deliver a landmark concert event that will officially launch the album.

The event will be branded as “TAMASHA LA UKRISTO NI UMOJA.” It will combine the power of faith, music, and community engagement in a way that resonates deeply with audiences. Album profits will be shared transparently, limited to sales recorded on the concert day, ensuring fairness and accountability.

This initiative is not just a one-time event; it is designed as the foundation for an annual recurring celebration, with Wasafi Media enjoying first refusal rights as exclusive partner each year. This ensures continuity, strengthens brand visibility, and positions Wasafi as a long-term leader in faith-inspired entertainment.

2. Problem Statement / Opportunity

Most previous concerts of this nature have been denomination based mostly on Catholic but this is set to bring together the Christian fratenity in its entirety.

This presents a clear opportunity for Wasafi Media

- Market Expansion: Tap into the vast and under-served gospel and Christian music audience in Tanzania and beyond.

- Revenue Generation:  highlight that this could very well be a recurring event preferably annually and Wasafi will reserve first refusal rights to be official partners yearly.In case of any received revenues from other sponsors(from Wasafi and from our side) we will aslo share in agreed shares

- Brand Enhancement: Associate the Wasafi brand with positive, inspirational, and community-building content, expanding its public image for your  image is already impressive and we are set to contribute to the already excellent image you have

4. Content Acquisition: Secure exclusive rights to broadcast and distribute a major gospel music event.

3. Proposed Solution & Partnership Overview

We propose that Wasafi Media becomes the official financier and producer of the "TAMASHA LA UKRISTO NI UMOJA" Concert Launch .

Roles and Responsibilities:

St. Monica Choir will provide

- The choir will provide the special song that bears the message of the event, going by the name “UKRISTO NI UMOJA”.

- The primary performing artist (the choir and soloists).

- Marketing support through our church and community networks.

- Creative input on the program and stage design to ensure alignment with our message.

Wasafi Media will provide

- Full Funding: Cover all costs associated with the concert (see Budget Outline).

2. Event Production: Secure a venue, manage stage setup, sound, lighting, and backline.

3. Promotion & Marketing: Leverage its powerful media platforms (TV, radio, social media) to promote the event nationally.

- Ticketing & Sales: Manage ticket sales through its established networks.

5. Media Coverage: Film and broadcast the concert for future TV specials or digital content.

4. Our Qualifications: The St. Monica Choir

Mt. Monica Choir is not just a musical group; we are a ministry with a track record of excellence.

- Musical Excellence: Comprised of dedicated and talented vocalists and musicians.

- Proven Product: We have already invested in the high-quality recording, mixing, and mastering of the "UKRISTO NI UMOJA" album, demonstrating our commitment and belief in the project.

- Captive Audience: We have a built-in support base of thousands of church members and a wider network of gospel music fans and we will bring with us other popular choirs that have wide engagement such as KMK Makuburi, Kwaya ya Mt Secilia- Makuburi and others

- Professionalism: We are organized and prepared to work diligently as partners to ensure the success of this event.

- 5.Project Timeline & Key Milestones

| - Phase | - Activity | Estimated Timeframe |
| --- | --- | --- |
| - Phase 1: Planning | - Contract Signing, Initial Creative Meetings | - 2 Weeks |
| - Phase 2: Pre-Production | - Venue Booking, Finalizing Budget, Marketing Campaign Launch | 4 Weeks |
| - Phase 3: Production | - Rehearsals, Technical Setup, Media Promotions | 3 Weeks |
| - Phase 4: Execution | - Concert Day | 1 Day |
| - Phase 5: Post-Event | - Settlement of Accounts, Media Distribution, Review | 2 Weeks |

Total Project Timeline: Approximately 10-12 Weeks from agreement signing.

6. Pricing & Budget Outline

The following is a preliminary estimate for the concert production. A detailed budget will be developed jointly upon agreement.

| Item | Estimated Cost (TZS) | Notes |
| --- | --- | --- |
| Venue Rental |  | For atleast 1000 capacity auditorium |
| Sound & Lighting |  | Professional grade for a high-quality experience |
| Backline & Instruments |  |  |
| Marketing & Promotion |  | Social media ads, radio spots, flyers |
| Staff & Security |  | Event staff, ushers, security personnel |
| Artiste Logistics |  | Transport, accommodation, hospitality |
| Contingency (10%) |  | For unforeseen expenses |
| Album copies |  |  |
| Total Estimated Budget |  |  |

Revenue Sharing Proposal (To be negotiated):

- Concert Ticket Sales: ......% Wasafi / .......% St. Monica

- Album Sales at Event: .......% St. Monica / ......% Wasafi

- Post-Event Digital Sales/Streaming: .......% Wasafi / ......% St. Monica (subject to distribution deals)

7. Terms and Conditions

- Intellectual Property: St. Monica Choir retains all copyrights to the album's musical compositions and recordings. Wasafi Media receives a license to use the material for promoting and broadcasting this specific event.

- Budget Management: Wasafi Media will manage the budget, with regular financial updates provided to the choir's leadership.

- Creative Control: While Wasafi leads production, both parties must mutually agree on the creative direction and program to maintain the artistic and spiritual integrity of the event.

4. Force Majeure: Standard clauses for unforeseen circumstances that prevent the event from occurring.

8. Agreement

This proposal signifies our sincere interest in partnering with Wasafi Media. We are confident that this collaboration will be a resounding success, delivering financial returns and positive cultural impact.

We eagerly await the opportunity to discuss this proposal further.

Signatures:

---

For St. Monica Choir

Name:

Title:

Date:

---

For Wasafi Media

Name:

Title:

Date: